## Cover
Cover
This Excel sheet contains the known issues in production as well as the other topics related to CESOP.
In case a sheet has been updated: - This sheet will be mentioned in the history; - The last column of the row that has been added or updated will provide the last KEL version where an update was made; - The related changes will be highlighted in green.
Date | 2024-05-24
Status | Version Submitted for Information
Version | 1.04
Author | SOFT-DEV
Public | DG TAXUD external
Confidentiality | Publicly available (PA)
History
Version | Date | Description
1.04 | 2024-05-24 | - Update of Known issues (KEL) sheet: Implementation expected date of CESOP v1.5.0.
1.03 | 2024-05-07 | - Update of Known issues (KEL) and Other topics sheets.
1.02 | 2024-04-26 | - Update of the Cover sheet; - Update of production date of v1.4.5 and related items; - Update of Known issues (KEL) and Other topics sheets.
1.01 | 2024-04-22 | - Addition of new columns; - Update of Known issues (KEL) and Other topics sheets.
1.00 | 2024-04-14 | First version of the Excel.

## Known issues (KEL)
Last update: | 2024-05-24
ID | Description | Impacted XSD version(s) | Impacted CESOP release(s) | Workaround(s) | Solution description | Implementation release | Implementation XSD version(s) | Comment | Implementation expected date | Implementation actual date | Last KEL update version
1 | The rule PS-BR-0010 (triggering the error code 30010), validates the following: "The business identifier ‘IN’ of the ‘Representative element must be different from the business identifier ‘IN’ of the ‘ReportingPSP’ element.". | v4.00 v4.01 v4.02 | Up to CESOP v1.4.x (included) | Add one or more characters to the representative, for instance like '-', '_' or '_REP'. | This rule will be removed. | CESOP v1.5.0 | N/A | This rule will be removed in CESOP v1.5.0 and will thus not be triggered anymore (regardless of the XSD version). | 2024-06-18 | - | 1.04
2 | The rule RP-BR-0030 (triggering the error code 40030), validates the following: "If the value of the ‘type’ attribute within the ‘AccountIdentifier’ element is equal to ‘IBAN, the format of the ‘AccountIdentifier’ value must be valid according to the following algorithm: - Check that the total IBAN length is correct as per the country. If not, the IBAN is invalid. [...]". This check against the length is causing issues because the country code reported in the CountryCode attribute may differ from the country code leading the account identifier, e.g.: <AccountIdentifier CountryCode=“BE" type="IBAN">LU…</AccountIdentifier> | v4.00 v4.01 v4.02 v4.03 | Up to CESOP v1.6 (included) | Use the same country code as the leading characters of the identifier, if IBAN type is selected. | This rule will be updated to validate the length against the country code within the account identifier instead of the country code attribute. | To be defined | N/A | - | - | - | 1.00
3 | The rule RT-BR-0050 (triggering the error code 45050), validates the following: "The 'TransactionIdentifier' element is not unique within the system.". However, the rejected TransactionIdentifier is not specified in the Validation Result Message received, so PSPs and MSs cannot identify the erroneous transaction. | N/A | Up to CESOP v1.4.4 (included) | - | The transaction identifier causing the issue will be part of the VLD message sent by CESOP. | CESOP v1.4.5 | N/A | Only impact on VLD message. | - | 2024-04-25 | 1.02
4 | Currently, in case different transaction dates are reported for a single transaction, CESOP validates if all dates in the payment data file concern the reporting period, via RT-BR-0030 (triggering the error code 45030). If at least one of the provided dates is out of the reporting period, then the file is partially rejected due to this business rule. | v4.00 v4.01 v4.02 | Up to CESOP v1.4.x (included) | For Q1 2024, only the transaction dates that are in this quarter shall be reported. | The rule will be updated to be triggered only if all dates are outside the reporting period. | CESOP v1.5.0 | N/A | This rule will be updated in CESOP v1.5.0 (regardless of the XSD version) | 2024-06-18 | - | 1.04
5 | The rules CM-BR-0100 (triggering the error code 20100) and RP-BR-0070 (triggering the error code 40070) validate the format of the PSP and the Representative identifier, respectively, when the type is set to "BIC". This rule performs the validation of the country code against the ISO-9362, including only 177 country codes. This implies that BIC reported with a country that is not part of the ISO-9362 will be considered as invalid. | v4.00 v4.01 v4.02 | Up to CESOP v1.5.x (included) | Use the PSPIdType "Other" instead of BIC. | The rule will be updated to validate the country code of all ISO-3166 codes. | CESOP v1.6.0 | N/A | This rule will be updated in CESOP v1.6.0 (regardless of the XSD version) | Q4 2024 | - | 1.01
6 | As of 1 July 2022, the Currency ISO CODE for 'SIERRA LEONE' is 'SLE'. In the Scheme ISO type file (XSD v4.00, v4.01 and v4.02), the currency mapped for 'SIERRA LEONE' is 'SLL'. | v4.00 v4.01 v4.02 | Up to CESOP v1.5.x (included) | Use the SLL currency. | The currency code of "Leone: SIERRA LEONE" in the isotypes.xsd will be updated from SLL to SLE. | CESOP v1.6.0 | v4.03 | The code SLL must thus be used with XSD v4.00, v4.01 and v4.02. Starting from XSD v4.03, the code SLE must be used. | Q4 2024 | - | 1.01
7 | The rule MH-BR-0020 (triggering the error code 10020), validates the following: "The ‘Timestamp’ element in the Payment Data message header cannot refer to a period starting in future. " However, depending on the time-server, this rule may be triggered while the timestamp has been properly set. | v4.00 v4.01 v4.02 | Up to CESOP v1.5.x (included) | When setting the timestamp, a small margin can be added. | This rule will be removed. | CESOP v1.6.0 | N/A | This rule will be removed in CESOP v1.6.0 and will thus not be triggered anymore (regardless of the XSD version). | Q4 2024 | - | 1.02
Formulas:
Implementation expected date = LOOKUP(Table1[[#This Row],[Implementation release]], Table3[Release],Table3[Implementation expected date])
Implementation actual date = LOOKUP(Table1[[#This Row],[Implementation release]], Table3[Release], Table3[Implementation actual date])

## Other topics
Last update: | 2024-05-24
ID | Description | Impacted XSD version(s) | Impacted CESOP release(s) | Workaround(s) | Solution description | Implementation release | Implementation XSD version(s) | Comment | Implementation expected date | Implementation actual date | Last KEL update version
1 | The PSPs submit payment data messages where the same payee is repeated several times, with one or few transactions, without aggregation | v4.00 v4.01 v4.02 | Up to CESOP v1.4.4 (included) | For the message not to be rejected, consolidation must be performed by the PSPs, before submitting the message to the National Tax Administrations. | A 99999 error will be triggered in case the same payee is reported at least twice in the same message: - Two reported payees are considered as being the same if they have all names the same and all accounts the same: - The reported names are considered the same if all the names and their respective attribute (nameType) exactly match; - The same applies for the account: it is considered the same if the account number and the respective attributes (CountryCode and type) exactly match; - Note that as from XSD version 4.03, several accounts will be allowed for a single reported payee. When this XSD version will be supported, the rule will consider a match if all reported accounts (thus the same account numbers and their respective attributes) exactly match. Also, starting from that version, a new attribute nameOther will be introduced for the name. This attribute, as the nameType one, will be taken into account for the rule as well. - If a matching criterion is not reported (e.g. the account is not reported), then no match will be considered and the rule will not be breached. | CESOP v1.4.5 | N/A | This rule will be added in CESOP v1.4.5 (regardless of the XSD version). | - | 2024-04-25 | 1.03
Formulas:
Implementation actual date = LOOKUP(Table13[[#This Row],[Implementation release]], Table3[Release], Table3[Implementation actual date])

## Param (hidden)
Release | Implementation expected date | Implementation actual date | Status | Confidentiality | Public
CESOP v1.4.5 | - | 2024-04-25 | Version Submitted for Review | Publicly available (PA) | DG TAXUD external
CESOP v1.5.0 | 2024-06-18 | - | Version Submitted for Acceptance |  | DG TAXUD internal
CESOP v1.6.0 | Q4 2024 | - | Version Submitted for Information
To be defined | - | - | Draft